## Sheet1
Start Date | End Date | Version | Phase / Milestone | Notes
2025-03-22 | 2025-03-31 | All | Initial requirement gathering | Identified copper cable theft problem, 48 V DC monitoring requirement SMS alert need, number of lines to monitor, installation locations, and stakeholder expectations.
2025-04-01 | 2025-04-10 | V1 | Concept & architecture design | Defined overall system architecture: line monitoring logic, power supply, basic enclosure, and GSM-based SMS alert mechanism.
2025-04-11 | 2025-05-10 | V1 | Hardware & firmware development | Designed prototype hardware, wrote initial firmware for line detection, error logic, and SMS triggering; basic bench testing on few lines.
2025-05-11 | 2025-05-25 | V1 | Integration & internal testing (V1 completed) | Assembled complete V1 unit with basic casing, tested end-to-end SMS alerts, verified line cut detection and error LED behaviour. V1 development cycle finished ~2025-05-25.
2025-05-26 | 2025-06-03 | V2 | Enhanced design & feature upgrade | Started redesign to support 8 monitoring ports, improved antenna and added Wi-Fi configuration features based on V1 feedback.
2025-06-04 | 2025-06-04 | V2 | V2 development completed | Finalised V2 hardware/firmware with 8 ports and configuration improvements. V2 development cycle finished ~2025-06-04.
2025-06-04 | 2025-06-25 | V2 | Pilot deployment – Rathnapura (start) | Same day as V2 completion, pilot test launched; installed units in the field, started real-world monitoring and log collection.
2025-06-25 | 2025-06-25 | V2 | Field rollout – 4 units handed over | Four V2 devices handed over to Mr. Sampath (Rathnapura) for extended pilot and operational use.
2025-06-26 | 2025-07-01 | V2 | Pilot tuning & feedback collection | Fine-tuned alert thresholds, checked reliability of SMS notifications, collected user feedback for usability and installation issues.
2025-07-02 | 2025-07-02 | V2 | Documentation & training | Created user guide for V2 and conducted an online explanation / training session for Mr. Sampath’s team.
2025-07-02 | 2025-08-18 | V3 | PCB & mechanical design cycle | Started V3 PCB development: compact PCB layout, BOM optimisation, improved connectors and mounting; parallel work on 3D printed housing design.
2025-08-18 | 2025-08-18 | V3 | V3 PCB design frozen & ordered | Completed V3 PCB design and placed fabrication order. V3 design phase milestone.
2025-08-19 | 2025-09-07 | V3 | Pre-build prep | Prepared firmware changes tailored for V3 board, finalised 3D housing model, planned test procedures while waiting for PCBs.
2025-09-08 | 2025-09-24 | V3 | PCB arrival & first build | PCBs received on 2025-09-08; assembled first V3 board, did power-on tests, line detection verification and enclosure fit checks.
2025-09-25 | 2025-09-25 | V3 | First fully-integrated V3 prototype | First V3 unit completed with 3D-printed housing, providing a more productised look and improved robustness. V3 initial build milestone.
2025-09-26 | 2025-10-11 | V3 | Lab & pre-field testing | Extended bench tests, long-run stability checks, verification of all 8 lines, refinement of firmware for alarms and error handling.
2025-10-12 | 2025-10-12 | V3 | Field testing – 2 units in Rathnapura | Two V3 devices deployed and tested in Rathnapura to compare against V2 units, focusing on reliability and enclosure durability.
2025-10-13 | 2025-10-29 | V3 → V4 | Feedback & modem upgrade planning | Analysed field feedback, identified need for modem upgrade and simplification; prepared SIM module change and UI improvements.
2025-10-30 | 2025-10-30 | V3/V4 | SIM module upgrade test | SIM module upgrade (to SIM800C-based approach) tested in Rathnapura to validate network performance and power behaviour. This becomes the base for V4.
2025-10-31 |  | V4 | Next-gen design cycle (in progress) | Ongoing design for V4: new compact PCB, reduced to 4 monitoring ports, SIM800C modem integration, addition of OLED display for status/config, more robust mechanical design and easier field configuration.
| 2025-11-24 | V4 | Complete PCB design | desig done
2025-11-24 | 2025-11-28 | V4 | PCB order place | order placed with jlc pcb
2025-12-08 | 2025-12-22 | V4 | Initial device fabrication
2025-12-22 | 2025-12-26 | V4 | Housing design & fabrication
2025-12-26 | 2026-01-09 | V4 | Initial testing
2026-01-09 | 2026-01-16 | V4 | Pilot Test
2026-01-16 | 2026-01-19 | V4 | Stickers & Branding
2026-01-19 | 2026-01-23 | V4 | Initial 4 devices distribute
2026-01-23 | 2026-01-30 | V4 | Confirm final version
2026-01-30 | 2026-02-02 | V4 | Bulk Ordering